## Gantt
| Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6
Actions | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Check points
Design
Basic Functionality
Viable Game
Extended Game
Architecture
Data model
Object model / interfaces
Component responsibilities
Model Extension
Database
Table design
First level design
Polygon creation
Gather images
Manually enter first level
Create user path stored procedure
Create new level stored procedure
Add extra basic levels
Extra functionality
Scoreboard
Different characteristics
Floating booty
Add advanced levels
Python
Build SVG display
Database class (connection, load data)
Game classes (e.g. obstacles etc)
Website class (Jinja template, render)
Validating Route
Interface with JavaScript
Communication with stored procedures
Extensions
Scoreboard
Different characteristics
Floating booty
Website
Initial display
HTML template
Styles
Animations (Lightning etc)
Validating Route
User inputs
JavaScript python interface
Displaying success or fail
Extensions
Scoreboard
Different characteristics
Floating booty
Testing
Load and display
Validating route
Accepting extra basic levels
Extensions
Documentation
Writeup
Presentation

## Weekly
| Week2 |  | Week3 | Week4
Display Task
Experiment Annimations, moving, lightning,explosion | MP/CC | Done | Abstract svg logic in to level and obstacles | Stored Proc Validation | ME/MP | Done
Collect SVG images | MP/CC | Done | Create db | Slight code modifications - hit wall? | LV | Done
|  |  | wire up db | Input forms | LV | Done
Framework Task |  |  | Js/Ajax moving | Test game logic | All | Done
Website Framework | ME/LV | Done |  | Note all actions done in db - tables, views, index etc Ensure have code | CC | Done
Jinja template - basic html | ME/LV | Done |  | Db system diagram (include views) | MP | Done
database connections | ME/LV | Done |  | Hardcode 10 moves | LV | Done | maybe drive db in future
helper classes | ME/LV | Done |  | Popup saying success, click next level | LV | Done
Permission shared area | ME | Done |  | score input in python | ME | Done
|  |  |  | jinga score param,levelid,startx,starty, max levels | ME | Done
To do |  |  |  | extend template for jinja | ME | Done
Setup in own area | CC/LV |  |  | 100 seconds per level - countdown | LV | Done
Build SVG output in level class (hard code) | MP/CC |  |  | Total score on page | LV | Done
polygon | MP/CC |  |  | Congratulations, you've finished - modal | LV | Mon | possibly be interval from db
island image | MP/CC |  |  | HTML page design | MP | Done
sea | MP/CC |  |  | Score board - db table | CC | Done
grid | MP/CC |  |  | SQL Script for adding score with variables | CC | Done
Boat | MP/CC |  |  | add total score to db python - new entry point (addScore), add method in db | ME | Mon
booty | MP/CC |  |  | Finish - - enter name, submit score - js/ajax submit | LV | Mon
Animations |  |  |  | SQL to display top 10 scores | CC | Done
Move boat hardcoded path | LV |  |  | Python generate top 10 scores and add to html - jinga | MP/CC | Done
lightning | LV |  |  | Remove diamond | CC | Done
Explore Ajax/Python/parameters/move class | ME |  |  | Level 5 | CC | Done
|  |  |  | annimations | LV | Mon
|  |  |  | lightning | MP | Mon
|  |  |  | DB - Spatial Index - fix bug | CC | Mon
|  |  |  | Unit Tests - fix Icon | MP | Mon
|  |  |  | Code comments - other code | MP
|  |  |  | E-R diagram - add total score | CC | Done
|  |  |  | Total Score table - db diagram | MP | Done
|  |  |  | Developers page/roles | MP/CC
Popups
|  |  |  | Small game improvements | LV
|  |  |  | Music to stop returning on for each level | LV
|  |  |  | Increase points/time | LV
|  |  |  | Add intro page | MP/CC
Make writeup outline - sections
Make presentation outline - sections
|  |  |  | JS error handling for move submission | LV
|  |  |  | Improve level names | CC
|  |  |  | Lightning | MP | Done
|  |  |  | explosion | MP
|  |  |  | sinking | MP