## Sheet1
| Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6
Actions | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Check points
Design
Basic Functionality
Viable Game
Extended Game
Architecture
Data model
Object model / interfaces
Component responsibilities
Model Extension
Database
Table design
First level design
Polygon creation
Gather images
Manually enter first level
Create user path stored procedure
Create new level stored procedure
Add extra basic levels
Extra functionality
Scoreboard
Different characteristics
Floating booty
Add advanced levels
Python
Build SVG display
Database class (connection, load data)
Game classes (e.g. obstacles etc)
Website class (Jinja template, render)
Validating Route
Interface with JavaScript
Communication with stored procedures
Extensions
Scoreboard
Different characteristics
Floating booty
Website
Initial display
HTML template
Styles
Animations (Lightning etc)
Validating Route
User inputs
JavaScript python interface
Displaying success or fail
Extensions
Scoreboard
Different characteristics
Floating booty
Testing
Load and display
Validating route
Accepting extra basic levels
Extensions
Documentation
Writeup
Presentation

## Sheet2
Week2
Display Task
Experiment Annimations, moving, lightning,explosion | MP/CC
Create simple Level class - hard coded
Contains rect, pics, boat
Render method - generate the SVG html
Add to render all special effects
Boat moving - hard coded route
Explore Ajax/Python/parameters
Collect SVG images | MP/CC
Framework Task
Website Framework | ME/LV
Jinja template - basic html | ME/LV
database connections | ME/LV
helper classes | ME/LV
Permission shared area