## Sheet1
| Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6
Actions | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Check points
Design | bar: Week2 F
Basic Functionality | bar: Week3 F
Viable Game | bar: Week4 F
Extended Game | bar: Week5 F
Architecture
Data model | bar: Week2 M to Week2 F
Object model / interfaces | bar: Week2 W to Week2 F
Component responsibilities | bar: Week2 M to Week2 F
Model Extension | bar: Week4 M to Week4 F
Database
Table design | bar: Week2 M to Week2 F
First level design | bar: Week2 W to Week2 F
Polygon creation | bar: Week2 T to Week2 F
Gather images | bar: Week2 T to Week2 F
Manually enter first level | bar: Week3 M to Week3 T
Create user path stored procedure | bar: Week3 W to Week3 T
Create new level stored procedure | bar: Week3 F to Week4 M
Add extra basic levels | bar: Week4 T to Week4 W
Extra functionality | bar: Week4 T to Week5 T
Scoreboard | bar: Week4 T
Different characteristics | bar: Week4 F to Week5 T
Floating booty | bar: Week4 F to Week5 M
Add advanced levels | bar: Week5 W to Week5 F
Python
Build SVG display | bar: Week2 M to Week3 T
Database class (connection, load data) | bar: Week2 M to Week2 W
Game classes (e.g. obstacles etc) | bar: Week2 T to Week3 T
Website class (Jinja template, render) | bar: Week2 M to Week2 T
Validating Route | bar: Week3 F to Week4 W
Interface with JavaScript | bar: Week3 F to Week4 M
Communication with stored procedures | bar: Week4 T to Week4 W
Extensions | bar: Week5 M to Week5 T
Scoreboard | bar: Week5 M
Different characteristics | bar: Week5 T to Week5 T
Floating booty | bar: Week5 T to Week5 W
Website
Initial display | bar: Week2 M to Week3 T
HTML template | bar: Week2 M to Week2 W
Styles | bar: Week2 M to Week2 W
Animations (Lightning etc) | bar: Week2 T to Week3 T
Validating Route | bar: Week3 F to Week4 W
User inputs | bar: Week3 F to Week4 M
JavaScript python interface | bar: Week3 F to Week4 M
Displaying success or fail | bar: Week4 T to Week4 W
Extensions | bar: Week5 M to Week5 T
Scoreboard | bar: Week5 M
Different characteristics | bar: Week5 T to Week5 T
Floating booty | bar: Week5 T to Week5 W
Testing
Load and display | bar: Week3 W to Week3 T
Validating route | bar: Week4 T to Week4 F
Accepting extra basic levels | bar: Week4 T to Week4 F
Extensions | bar: Week5 F to Week6 M
Documentation
Writeup | bar: Week5 M to Week5 F
Presentation | bar: Week5 W to Week6 M